## Summary
Development Branch Assessment — sreme19’s changes vs main
Generated 2026-06-26 • development is 11 commits ahead of main, 0 behind • scope: the 3 feature commits authored by sreme19
Overall verdict
LOW RISK — sreme19’s 3 commits are contract-preserving. His changed files have 0 type errors (svelte-check) and 0 analyzer errors (flutter analyze). The scary repo-wide numbers (22 type errors, ~62 failing tests, 82 lints) are ALL pre-existing tech-debt in files he never touched — verified identical between main and development.
What sreme19 actually shipped (3 commits, 2026-06-26)
Commit | Title
98290ec | feat(mobile): first-class AI Bestie identity in man’s chat thread | Mobile UI
364ed93 | feat(attention): Craving Attention auto-engages her AI Bestie + forms match | Backend logic
2e0a786 | feat(mobile): Pass 2 — AI/human distinction, hand-off notice, Wingman labeling | Mobile UI
Note: the 4th non-merge dev commit, 4ce526c “fix disconnected dealbreaker table”, is YOURS (0nelang), not sreme19’s. The rest of the 11 are merge commits.
Key callouts — who to ping & what to watch
★ #1 to verify | Your (0nelang) “reply with Bestie” fix was refactored into a shared helper (attention-bestie.ts). The endpoint still returns {ok, matchId} — same contract mobile expects. Smoke-test the hand-off button.
Ping ekasaputra0324 | sreme19 edited his primary file chat_list_screen.dart (he owns 27 of its commits) and the shared conversation_screen.dart (+292 lines). Risk is visual/merge, not API. Have him eyeball the chat list + thread UI.
Minor code smell | flutter analyze flags unused _imageUploading field & _pickAndSendImage method in conversation_screen.dart after his Pass-2 edit — confirm in-chat image send still works (possible orphaned code).
FYI — broader delta | development also contains YOUR dealbreaker fix (pool-registry.ts) and a new hard-nos endpoint + migration — not part of sreme19’s 3 commits, but they ride along when you merge to main.

## File Matrix
File | Feature / Commit | What sreme19 changed | All-time owners | Co-owner to ping | Risk | What to verify | ✓ Verified
src/lib/server/attention-bestie.ts | 364ed93 | NEW shared helper engageBestieForAttention() — extracted the bestie hand-off logic out of your reply endpoint into one reusable function. | sreme19 (new) | — | None | Logic forms a mutual match (ai_bestie_active=true), seeds convo w/ sender note, marks msg handled, triggers reply. | TODO
src/routes/api/verified-vibe/attention/+server.ts | 364ed93 | +16 lines: on a man’s Craving Attention send, auto-calls engageBestieForAttention so her AI Bestie replies automatically. | sreme19 (5), ekasaputra0324 (1) | ekasaputra | Low-Med | Send a Craving Attention → match auto-forms + Bestie replies. Confirm GET attention lists still work. | TODO
src/routes/api/verified-vibe/attention/reply-with-bestie/+server.ts | 364ed93 | Gutted −110 lines → now a thin wrapper calling the shared helper. Same response {ok, matchId}. | sreme19 (1), 0nelang (1) | YOU (0nelang) | Medium | ★ PRIORITY: tap “reply with Bestie” in app → match forms + Bestie replies, exactly as after your fix. | TODO
mobile/lib/conversation_screen.dart | 98290ec, 2e0a786 | +292 lines: first-class AI Bestie identity in man’s thread, AI/human distinction, hand-off notice, Wingman labeling. | sreme19 (17), ekasaputra0324 (11) | ekasaputra | Med-High | Bestie messages clearly labeled AI; hand-off notice shows; no regression to chat layout. NB: analyzer flags unused image-send code — test image send. | TODO
mobile/lib/chat_list_screen.dart | 364ed93 | +16 lines: handles BESTIE_HANDLED_MARKER so auto-engaged threads render correctly in the chat list. | ekasaputra0324 (27), sreme19 (12), 0nelang (2) | ekasaputra (his file) | High-overlap | Chat list renders auto-engaged Bestie threads; unread counts intact (ekasaputra’s recent area). | TODO
mobile/pubspec.yaml | 2e0a786 | Build/version number bump for tester distribution. | sreme19 (48), ekasaputra0324 (19) | — | Low | Version higher than current TestFlight build; watch for merge conflict on the version line. | TODO
docs/bestie-thread-gap-inventory.md | 98290ec, 2e0a786 | NEW doc — sreme19’s own inventory of gaps in the bestie-thread work. | sreme19 (new) | — | None | Read-only — captures his intent & known gaps. | TODO

## Verification
Check | Command | Covers | Result | Details
Type check (backend) | npm run check | sreme19’s 3 src/ files | PASS | 0 errors in his files. The 22 repo-wide errors are in files he never touched (logAppError, admin/monitoring, ai-bestie/chat, ai-wingman/chat, chat/send, like, pass) — identical on main, pre-existing.
Unit/component tests | npm run test | backend + components | PASS | No failing suite touches his code. Failing: chat-interface(24), DiscoveryCard.mobile(19), PhotoUploadStep(17), PersonalityEditor(2) — none differ between main↔development and none import his modules ⇒ pre-existing. (PhotoUploadStep hangs on a fake-timer issue.)
Static analysis (mobile) | cd mobile && flutter analyze | sreme19’s 2 .dart files | PASS | 0 errors. 82 info/warning lints repo-wide. In his files: 3 info lints + 2 warnings in conversation_screen.dart (unused _imageUploading field & _pickAndSendImage method) — non-breaking; check for orphaned image-send code.
Widget tests (mobile) | cd mobile && flutter test | mobile widgets | TODO | Optional, not run here. Existing: regression_test.dart, widget_test.dart, onboarding_questions_test.dart. Run locally to be thorough.
Smoke: reply-with-Bestie | manual in app | your fix / endpoint contract | TODO | ★ Highest value. Tap “reply with Bestie” on a received attention → confirm a match forms and the AI Bestie posts the first reply.
Smoke: Craving-Attention auto-engage | manual in app | new feature (364ed93) | TODO | Send a Craving Attention as a man → confirm her AI Bestie auto-engages, a match is formed, and Bestie replies without her tapping anything.